## Tabelle1
Sprint Review Protocol
Sprint No: |  | 4
Date & Time |  | 2022-05-24
Group Number |  | 8
Participant 1 |  | Faltas Patrick
Participant 2 |  | Müller Oliver
Participant 3 |  | Njeru Paula
Participant 4 |  | Porubsky Matus
Participant 5 |  | Wiedermann Gabriel
Mentor |  | Parg Manuel-Christopher
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | [Porubsky] [Müller] Research movement in unity (layer masks, transformations, object relationships) | 5 | 5 | 0
2 | [Porubsky] [Müller] Implement movement in unity (with scripts) | 10 | 8 | -2 |  |  | selection fehlt noch
3 | [Faltas] [Wiedermann] implementing the fighting | 15 | 12 | -3 |  |  | selection fehlt noch
4 | [Porubsky] Create Prefabs for collision | 1 | 1 | 0
5 | [Porubsky] Create brushes for Prefabs | 1 | 2 | 1
6 | [Müller] Reworking some assets | 1 | 1 | 0
7 | [Paula] Create Pause Menu in Unity | 1 | 1 | 0
8 | [Alle] Meetings | 4 | 4 | 0
9 |  |  |  | 0
10 |  |  |  | 0
11 |  |  |  | 0
12 |  |  |  | 0
13 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
13 |  |  |  | -4 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol