## Tabelle1
Sprint Review Protocol
Sprint No: |  | 4
Date & Time |  | 2022-05-24
Group Number |  | 8
Participant 1 |  | Faltas Patrick
Participant 2 |  | Müller Oliver
Participant 3 |  | Njeru Paula
Participant 4 |  | Porubsky Matus
Participant 5 |  | Wiedermann Gabriel
Mentor |  | Parg Manuel-Christopher
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | [Porubsky] Build Grid and established tilesets | 4 | 4 | 0
2 | [Porubsky] Wrote movement script, implemented grid movement | 3 | 3.5 | 0.5
3 | [Faltas] Watching Unity Tutorials, trying to implement what was learnt | 3 | 3 | 0
4 | [Faltas] Establishing Rules | 1 | 2 | 1 |  |  | rules are up for review. possible changes to be discussed
5 | [Faltas, Wiedermann] Implementing Unit Classes | 10 | 6 | -4
6 | [Faltas, Wiedermann] Implementing Terrain Classes | 10 | 6 | -4
7 | [Faltas, Wiedermann] Implementing Fight System | 2 | 2 | 0 |  |  | Started, not yet finished, but expected to finish by end of next Sprint
8 | [Wiedermann] Watching Viedeos about programming in c# and how to write classes (Interfaces/abstrakteKlassen/…) | 2 | 2 | 0
9 | [Wiedermann] Implement the classes in a similiar way at the URL diagramm | 3 | 2 | -1
10 | [Paula]: Watched YouTube video tutorial on how to display player stats on unity | 1 | 1 | 0
11 | [Paula]: Youtube tutorial on creating a character stats window using classes in c# | 1 | 1.5 | 0.5
12 | [Paula]: Created simple stats window in unity using classes in c#(based on tutorial) | 2 | 2 | 0
13 | [Müller] designing remaining sprites for the units and their animation | 3 | 3.5 | 0.5
14 | [Müller] designing missing tiles | 1 | 1 | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
14 |  |  |  | -6.5 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol